## Sheet1
Weekly Project Report
Report Updated through: 8/25/2021
Project Name | Request Type | Project Manager | PSI | PCI | Meeting Scope | Remaining Budget | Original Approved Budget | Current Approved Budget | Current LTD Spend | Sprint 0 Cost | TD Cost | UNCommitted Cost | Project Start Date | Original Complete Date | Current Approved Complete Date | PM Estimated Complete Date | Directorate | Division
Project Name | New Application | PMO Name | R | G | Yes | 27230.65 | 650504 | 650504 | 663911.85 | 0 | 0 | 40638.5 | 2020-05-11 08:00 | 2021-06-30 17:00 | 2021-09-07 17:00 | 2021-09-07 17:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | System Enhancement | PMO Name | Y | G | Yes | 33126.41 | 249000 | 249000 | 220208.59 | 637.5 | 21582.92 | 4335 | 2020-05-08 | 2021-09-24 17:00 | 2021-09-24 17:00 | 2021-09-24 17:00 | Chief Financial Officer | Fiscal
Project Name | Maintenance | PMO Name | G | G | Yes | 41947.5 | 68000 | 68000 | 26392.5 | 0 | 0 | 340 | 2021-07-01 08:00 | 2021-10-14 17:00 | 2021-10-29 17:00 | 2021-10-29 17:00 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 134406.25 | 261120 | 261120 | 127011.25 | 0 | 0 | 297.5 | 2021-07-01 08:00 | 2021-10-14 17:00 | 2021-10-13 17:00 | 2021-10-13 17:00 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 156697.5 | 256530 | 256530 | 99917.5 | 0 | 0 | 85 | 2021-07-01 08:00 | 2021-10-14 17:00 | 2021-10-14 17:00 | 2021-10-14 17:00 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 45050 | 95200 | 95200 | 50490 | 0 | 0 | 340 | 2021-07-01 08:00 | 2021-10-14 17:00 | 2021-10-29 17:00 | 2021-10-29 17:00 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 71867.5 | 115940 | 115940 | 47812.5 | 0 | 0 | 3740 | 2021-06-28 08:00 | 2021-10-14 17:00 | 2021-10-14 17:00 | 2021-10-14 17:00 | Deputy Chief Engineer | Construction
Project Name | System Enhancement | PMO Name | G | G | Yes | -199593.75 | 3740000 | 3740000 | 3939593.75 | 0 | 0 | 0 | 2018-02-12 08:00 | 2021-10-29 17:00 | 2021-10-29 17:00 | 2021-10-29 17:00 | Chief of Policy | Environmental
Project Name | Maintenance | PMO Name | G | G | Yes | 209587.5 | 305000 | 305000 | 128494.5 | 0 | 0 | 33082 | 2021-07-13 08:00 | 2021-11-05 17:00 | 2021-11-05 17:00 | 2021-11-05 17:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 165410 | 208335 | 208335 | 42925 | 0 | 0 | 0 | 2021-08-02 08:00 | 2021-11-15 17:00 | 2021-11-19 17:00 | 2021-11-19 17:00 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 118830 | 155295 | 155295 | 37145 | 0 | 0 | 680 | 2021-08-02 08:00 | 2021-11-15 17:00 | 2021-11-15 17:00 | 2021-11-15 17:00 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 46920 | 55420 | 55420 | 8500 | 0 | 0 | 0 | 2021-08-02 08:00 | 2021-11-15 17:00 | 2021-11-15 17:00 | 2021-11-15 17:00 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 54260.44 | 194127.94 | 194127.94 | 141185 | 0 | 25457.5 | 1317.5 | 2021-02-10 | 2021-12-03 12:00 | 2021-12-03 12:00 | 2021-12-03 12:00 | Chief of Administration | Office of Information Security
Project Name | New Application | PMO Name | G | G | Yes | 133602.5 | 400000 | 400000 | 266397.5 | 0 | 0 | 0 | 2020-09-01 08:00 | 2021-12-17 17:00 | 2021-12-17 17:00 | 2021-12-17 17:00 | Chief Financial Officer | Fiscal
Project Name | Maintenance | PMO Name | G | G | Yes | 258522.91 | 465115.41 | 465115.41 | 341221.88 | 7395 | 153924.38 | 134629.38 | 2020-10-22 08:00 | 2021-12-21 17:00 | 2021-12-21 17:00 | 2021-12-21 17:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 167312.06 | 479015.31 | 479015.31 | 335099.5 | 5525 | 0 | 23396.25 | 2021-01-05 08:00 | 2022-01-03 12:00 | 2021-12-21 12:00 | 2021-12-21 12:00 | Chief of Maintenance and Operations | Asset Management
Project Name | Maintenance | PMO Name | G | G | Yes | 389461.17 | 729630.13 | 729630.13 | 343462.71 | 5525 | 0 | 3293.75 | 2020-10-13 08:00 | 2022-01-10 17:00 | 2022-01-10 12:00 | 2022-01-10 12:00 | Commissioner | Human Resources
Project Name | System Enhancement | PMO Name | G | G | Yes | 48644.81 | 203897.31 | 203897.31 | 155252.5 | 2210 | 0 | 0 | 2021-01-05 08:00 | 2022-01-21 17:00 | 2022-03-22 12:00 | 2022-03-22 12:00 | Chief of Maintenance and Operations | Land Use
Project Name | Maintenance | PMO Name | G | G | Yes | 147244.65 | 217260 | 217260 | 70015.35 | 0 | 0 | 0 | 2021-06-01 08:00 | 2022-01-27 12:00 | 2022-01-27 12:00 | 2022-01-27 12:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 469333.75 | 600000 | 600000 | 138316.25 | 0 | 0 | 7650 | 2021-05-24 08:00 | 2022-01-31 17:00 | 2022-01-31 17:00 | 2022-01-31 17:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 1727864.38 | 1950971.88 | 1950971.88 | 200030 | 0 | 0 | -23077.5 | 2021-02-22 08:00 | 2022-03-03 12:00 | 2022-03-03 12:00 | 2022-03-03 12:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | System Enhancement | PMO Name | G | G | Yes | 863392.52 | 1634234.5 | 1634234.5 | 789138.23 | 22090.99 | 778491.98 | 18296.25 | 2021-03-15 08:00 | 2022-04-29 12:00 | 2022-04-29 17:00 | 2022-04-29 17:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 1229569.1 | 2675146.25 | 2675146.25 | 1468002.98 | 156498.25 | 0 | 22425.83 | 2020-09-02 08:00 | 2022-06-15 17:00 | 2022-06-21 09:00 | 2022-06-21 09:00 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 1040246.48 | 1280801.25 | 1280801.25 | 258702.27 | 23162.5 | 0 | 18147.5 | 2021-04-05 08:00 | 2022-08-25 17:00 | 2022-08-25 17:00 | 2022-08-25 17:00 | Chief Financial Officer | Infrastructure Investment
Project Name | New Application | PMO Name | G | G | Yes | 5396153 | 5725738.5 | 5725738.5 | 329585.5 | 0 | 0 | 0 | 2020-09-29 08:00 | 2023-07-31 17:00 | 2023-07-31 17:00 | 2023-07-31 17:00 | Commissioner | Human Resources
Project Name | System Enhancement | PMO Name | G | G | Yes | 3544836.7 | 3732652 | 3732652 | 187815.3 | 0 | 0 | 0 | 2021-05-03 | 2023-08-31 17:00 | 2023-08-31 17:00 | 2023-08-31 17:00 | Chief Financial Officer | Infrastructure Investment
Project Name | Estimated Start
Project Name
Project Name | 2021-09-01
Project Name | 2021-10-01
Project Name | 2021-10-31
Project Name | 2021-11-30
Completed Project Q1 | Request Type | PMO Name | PSI | PCI | Meeting Scope | Remaining Budget | Original Approved Budget | Current Approved Budget | Current LTD Spend | Sprint 0 Cost | TD Cost | UNCommitted Cost | Project Start Date | Original Complete Date | Current Approved Complete Date | Actual Complete Date | Directorate | Division
Project Name |  | PMO Name
Project Name | Maintenance | PMO Name | G | G | Yes | 24572.65 | 66937.5 | 66937.5 | 42364.85 | 0 | 0 | 0 | 2021-04-01 08:00 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 10883.4 | 182070 | 182070 | 171186.6 | 0 | 0 | 0 | 2021-04-01 08:00 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 26362.75 | 219555 | 219555 | 193192.25 | 0 | 0 | 0 | 2021-04-01 08:00 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 25585 | 93712.5 | 93712.5 | 68127.5 | 0 | 0 | 0 | 2021-04-01 08:00 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 30515 | 113985 | 113985 | 95880 | 12410 | 0 | 12410 | 2021-04-01 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Deputy Chief Engineer | Construction
Project Name | Maintenance | PMO Name | G | G | Yes | 146986.25 | 605455 | 605455 | 467648.75 | 0 | 0 | 9180 | 2020-11-30 08:00 | 2021-07-14 17:00 | 2021-07-14 17:00 | 2021-07-14 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 714382.5 | 973930 | 973930 | 268912.18 | 8032.5 | 137105 | 9364.68 | 2020-10-01 08:00 | 2021-09-27 17:00 | 2021-09-27 17:00 | 2021-07-14 | Chief of Technology and Business Strategy | Information Technology
Project Name | System Enhancement | PMO Name | G | G | Yes | 249270.82 | 3500000 | 3500000 | 3250729.18 | 3740 | 577775.84 | 0 | 2019-06-24 08:00 | 2021-08-27 08:00 | 2021-08-27 08:00 | 2021-07-21 | Chief Financial Officer | Infrastructure Investment
Project Name | Maintenance | PMO Name | G | G | Yes | 14195 | 202385 | 202385 | 190867.5 | 124185 | 0 | 2677.5 | 2021-03-08 08:00 | 2021-08-30 17:00 | 2021-08-30 17:00 | 2021-07-26 | Chief of Technology and Business Strategy | Information Technology
Project Name | Maintenance | PMO Name | G | G | Yes | 33405 | 211650 | 211650 | 178245 | 0 | 0 | 0 | 2021-05-03 08:00 | 2021-08-13 17:00 | 2021-08-13 17:00 | 2021-08-09 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 40290 | 157760 | 157760 | 117470 | 0 | 0 | 0 | 2021-05-03 08:00 | 2021-08-13 17:00 | 2021-08-13 17:00 | 2021-08-09 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 11815 | 56100 | 56100 | 44370 | 0 | 0 | 85 | 2021-05-03 08:00 | 2021-08-13 17:00 | 2021-08-13 17:00 | 2021-08-09 | Chief of Maintenance and Operations | Traffic Engineering
Project Name | Maintenance | PMO Name | G | G | Yes | 94520 | 328100 | 328100 | 247180 | 224442.5 | 0 | 13600 | 2021-02-24 08:00 | 2021-08-30 17:00 | 2021-08-30 17:00 | 2021-08-10 | Chief of Technology and Business Strategy | Information Technology
Formulas:
Request Type = [Request Type, row above]+30